## Sheet1
Date | Day | Team Member | To Do Today | Did Today | Do by next meeting
2017-10-25 | Wednesday | Garima | start exploring computation algorithms for translating sensor data into recommendations |  | have data processing concept complete for sensor data --> recommendations
2017-10-25 | Wednesday | Brian | Start looking into the sensors (hardware)
2017-10-25 | Wednesday | John | Begin WHO IAQ criteria |  | Create recommendation tree, 3-4 recs, criteria, and their predicted effect
2017-10-25 | Wednesday | Matt | Look into REST API, iphone app building using Xcode |  | Figure out how to send collected data from SD Card to a web app
2017-11-01 | Wednesday | Garima | connectivity, google maps api
2017-11-01 | Wednesday | John | Find an SD port, get "Jacobs Box" laser cutter template, update listen and process to use real limits